## Estimate Summary
PROJECT ESTIMATION
|  |  |  | NOTE: | 1 Point = 6 hours
1 Story Point = $600
| Scope Item | Effort in Points | (%) | Category
Development Effort = Analysis + Build (Code & Unit Test) + Code Reviews
QA Effort = Analysis, Planning, Test case design, Test data creation, Execution
| Project Management - 30% of total Development effort |  |  | PM
| Technical Architecture - 12% of total Development effort |  |  | ARCH
| Defect Resolution Dev 8% of total Development effort |  |  | DEV
| Defect Resolution QA 8% of total QA effort |  |  | QA
| Regression Testing - 15% of total QA effort |  |  | QA
| Test Automation - 10% of total QA effort |  |  | QA
| Environment Setup - 3% of total Development effort |  |  | INFRA
| Performance Testing - 5% of total QA effort |  |  | QA
| Code Quality/Tech Debt - 10% of total Development effort |  |  | DEV
| Integration Testing | 12 |  | QA
| End to End Testing | 8 |  | QA
| Dev Support during Testing - 8% of total Development effort | 0 |  | DEV
| Post Go-Live Support - 10% of total effort | 0 |  | SUP
| Release Coordination - 3% of total Development effort |  |  | REL
| Deployment Activities - 4% of total Development effort |  |  | REL
| Infrastructure Setup - 5% of total Development effort |  |  | INFRA
| Documentation - 2% of total Development effort |  |  | DOC
| TOTAL Estimate (In Points): | 248.5 | 100.00%
Total Estimate ($):
| Total Dev Effort (In Points): | 120
Total Dev Effort ($):
| Total QA Effort (In Points): | 72
Total QA Effort ($):

## Task Breakdown
Ticket ID | Task Description | Story Points | Notes | Module Affected
| Slot optimization algorithm SVC6010 Velocity-based assignment Space optimization | DEV: 45 Points QA: 28 Points | Core engine | Warehouse
| Velocity analysis engine SVC6011 ABC classification Trend analysis | DEV: 30 Points QA: 18 Points | Analytics | Warehouse
| Pick path calculator SVC6012 Path optimization Distance minimization | DEV: 25 Points QA: 15 Points | Optimization | Warehouse
| Batch jobs for re-slotting Weekly recommendations Utilization reports | DEV: 12 Points QA: 7 Points | Scheduled | Batch
| Database and configuration Slot tables Velocity metrics | DEV: 8 Points QA: 4 Points | Setup | Database

## QA Estimates
QA Estimation Details
Total QA Points: | 72

## Dev Estimates
Development Estimation Details
Total Dev Points: | 120

## Assumptions and Risks
ASSUMPTIONS
• Warehouse layout data is accurate and current
• SKU velocity data available for past 12 months
• RF scanners support new slot assignments
• Warehouse staff trained on new procedures
DEPENDENCIES
• WMS upgrade to support dynamic slotting
• Historical sales data migration completed
• Warehouse mapping verification
RISKS
Risk | Probability | Impact | Mitigation
Disruption during re-slotting activities | Medium | High | Phased rollout during low-volume periods
Data accuracy of warehouse dimensions | Low | Medium | Physical verification before go-live
Picker acceptance of new slot locations | Medium | Low | Training and gradual transition

## Sizing Guidelines
Story Point Sizing Guidelines
Points | Description
1-2 Points | Small, well-understood changes
3-5 Points | Medium complexity, some unknowns
6-8 Points | Complex changes, multiple components
9-13 Points | Very complex, requires research
13+ Points | Should be broken down into smaller stories

## Budget Summary
Budget Summary
Total Project Budget:
Development:
QA:

## Reference Data
Reference Data
Hourly Rate: $100
Points to Hours: 1 Point = 6 Hours
Story Point Value: $600

## Jira Stories
PRJ-10053 - Jira Stories
Story Key | Summary | Description | Story Points | Priority | Status | Assignee | Sprint | Component | Labels
WHS-3001 | Implement slot optimization algorithm (SVC6010) | As a system, I need to assign optimal warehouse slots based on SKU velocity and pick efficiency. Acceptance Criteria: - ABC classification (Top 20% = A, Next 30% = B, Bottom 50% = C) - Zone assignment: Golden/Standard/Bulk zones - Slot selection based on dimensions and proximity to staging - Support for FIFO rotation requirements - Bin packing algorithm for space optimization | 13 | High | To Do | U.Jackson | Sprint 1 | Warehouse Management | backend, algorithm, optimization, slotting
WHS-3002 | Build velocity analysis engine (SVC6011) | As a system, I need to analyze SKU velocity for slotting decisions. Acceptance Criteria: - Calculate velocity from 12-month historical sales data - ABC classification logic - Trend analysis for seasonal products - Re-classification triggers (velocity change > 25% over 4 weeks) - Export velocity reports | 8 | High | To Do | V.Harris | Sprint 1 | Warehouse Management | backend, analytics, velocity, classification
WHS-3003 | Create pick path calculator (SVC6012) | As a system, I need to calculate optimal pick paths to minimize travel time. Acceptance Criteria: - Distance calculation from staging area - Pick path optimization algorithm - Support for different picking strategies (zone, batch, wave) - Integration with warehouse layout data - Path simulation and testing capability | 8 | Medium | To Do | W.Clark | Sprint 2 | Warehouse Management | backend, optimization, pick-path, algorithm
WHS-3004 | Develop weekly re-slotting batch job (BTH6010) | As an operations team, I need weekly re-slotting recommendations based on velocity changes. Acceptance Criteria: - Scheduled job runs every Sunday at 02:00 AM - Identify SKUs requiring re-slotting - Generate recommended slot changes - Calculate disruption impact and priority - Email recommendations to warehouse managers | 5 | Medium | To Do | X.Rodriguez | Sprint 2 | Batch Processing | backend, batch, re-slotting, scheduler
WHS-3005 | Build zone utilization reporting (BTH6011) | As a warehouse manager, I need daily reports on zone utilization. Acceptance Criteria: - Daily utilization report by zone - Capacity alerts for zones exceeding thresholds - Trending analysis (weekly/monthly) - Visual heat maps of warehouse utilization - Export to Excel for analysis | 5 | Low | To Do | Y.Lewis | Sprint 3 | Reporting | backend, reporting, utilization, dashboard
WHS-3006 | Design warehouse slot database schema | As a system, I need database tables for slot assignments and velocity metrics. Acceptance Criteria: - Create TBL_SLOT_ASSIGN with assignment history - Create TBL_VELOCITY with SKU velocity metrics - Create TBL_ZONE_CONFIG for zone capacity rules - Indexes on SKU, warehouse, zone - Migration scripts and seed data | 5 | High | To Do | Z.Walker | Sprint 1 | Database | backend, database, schema, migration