## Estimate Summary
PROJECT ESTIMATION
|  |  |  | NOTE: | 1 Point = 6 hours
1 Story Point = $600
| Scope Item | Effort in Points | (%) | Category
Development Effort = Analysis + Build (Code & Unit Test) + Code Reviews
QA Effort = Analysis, Planning, Test case design, Test data creation, Execution
| Project Management - 30% of total Development effort |  |  | PM
| Technical Architecture - 12% of total Development effort |  |  | ARCH
| Defect Resolution Dev 8% of total Development effort |  |  | DEV
| Defect Resolution QA 8% of total QA effort |  |  | QA
| Regression Testing - 15% of total QA effort |  |  | QA
| Test Automation - 10% of total QA effort |  |  | QA
| Environment Setup - 3% of total Development effort |  |  | INFRA
| Performance Testing - 5% of total QA effort |  |  | QA
| Code Quality/Tech Debt - 10% of total Development effort |  |  | DEV
| Integration Testing | 12 |  | QA
| End to End Testing | 8 |  | QA
| Dev Support during Testing - 8% of total Development effort | 0 |  | DEV
| Post Go-Live Support - 10% of total effort | 0 |  | SUP
| Release Coordination - 3% of total Development effort |  |  | REL
| Deployment Activities - 4% of total Development effort |  |  | REL
| Infrastructure Setup - 5% of total Development effort |  |  | INFRA
| Documentation - 2% of total Development effort |  |  | DOC
| TOTAL Estimate (In Points): | 312.8 | 100.00%
Total Estimate ($):
| Total Dev Effort (In Points): | 155
Total Dev Effort ($):
| Total QA Effort (In Points): | 88
Total QA Effort ($):

## Task Breakdown
Ticket ID | Task Description | Story Points | Notes | Module Affected
| EDI message parser SVC7010 850/855/856/810 support X12 format handling | DEV: 40 Points QA: 22 Points | 850/855/856/810 | EDI
| PO transmission service SVC7011 Outbound 850 messages Acknowledgment handling | DEV: 35 Points QA: 20 Points | Outbound | EDI
| ASN processor SVC7012 Inbound 856 processing Receiving integration | DEV: 35 Points QA: 20 Points | Inbound | EDI
| Invoice matcher SVC7013 3-way matching Discrepancy handling | DEV: 30 Points QA: 18 Points | 3-way match | EDI
| Batch jobs and retry logic Daily transmission Error recovery | DEV: 15 Points QA: 8 Points | Error handling | Batch

## QA Estimates
QA Estimation Details
Total QA Points: | 88

## Dev Estimates
Development Estimation Details
Total Dev Points: | 155

## Assumptions and Risks
ASSUMPTIONS
• Suppliers support EDI X12 standard
• VAN connectivity established
• EDI transaction sets 850, 855, 856, 810 required
• Supplier trading partner agreements signed
DEPENDENCIES
• VAN service provider contract executed
• Supplier onboarding process defined
• Procurement system EDI-ready
RISKS
Risk | Probability | Impact | Mitigation
Supplier EDI capability varies | High | Medium | Tiered onboarding approach
Message format inconsistencies | Medium | Medium | Robust parsing with error reporting
VAN service reliability | Low | High | SLA monitoring and backup provider

## Sizing Guidelines
Story Point Sizing Guidelines
Points | Description
1-2 Points | Small, well-understood changes
3-5 Points | Medium complexity, some unknowns
6-8 Points | Complex changes, multiple components
9-13 Points | Very complex, requires research
13+ Points | Should be broken down into smaller stories

## Budget Summary
Budget Summary
Total Project Budget:
Development:
QA:

## Reference Data
Reference Data
Hourly Rate: $100
Points to Hours: 1 Point = 6 Hours
Story Point Value: $600

## Jira Stories
PRJ-10054 - Jira Stories
Story Key | Summary | Description | Story Points | Priority | Status | Assignee | Sprint | Component | Labels
EDI-4001 | Build EDI message parser for X12 formats (SVC7010) | As a system, I need to parse EDI X12 messages (850, 855, 856, 810) from suppliers. Acceptance Criteria: - Support for EDI 850 (Purchase Order) - Support for EDI 855 (PO Acknowledgment) - Support for EDI 856 (Advance Ship Notice) - Support for EDI 810 (Invoice) - X12 format validation and error handling - Configurable parsing rules per supplier | 13 | High | To Do | A.Young | Sprint 1 | EDI Integration | backend, edi, x12, parser
EDI-4002 | Implement PO transmission service (SVC7011) | As a procurement system, I need to send purchase orders to suppliers via EDI 850. Acceptance Criteria: - Generate EDI 850 from internal PO format - VAN connectivity for transmission - Transmission confirmation tracking - Retry logic for failed transmissions - Support for multiple VAN protocols (AS2, FTP, HTTPS) | 8 | High | To Do | B.King | Sprint 1 | EDI Integration | backend, edi, outbound, van
EDI-4003 | Develop ASN processor (SVC7012) | As a receiving system, I need to process inbound EDI 856 advance ship notices. Acceptance Criteria: - Parse EDI 856 messages - Validate against original PO - Create receiving documents - Update inventory expectations - Exception handling for mismatches - Integration with WMS receiving module | 8 | High | To Do | C.Wright | Sprint 2 | EDI Integration | backend, edi, inbound, asn
EDI-4004 | Build invoice matching service (SVC7013) | As a finance system, I need 3-way matching of EDI 810 invoices against PO and receipt. Acceptance Criteria: - Parse EDI 810 invoice messages - 3-way match: PO vs Receipt vs Invoice - Tolerance checking for quantity/price variances - Auto-approval for exact matches - Exception queue for variances - Integration with AP system | 8 | Medium | To Do | D.Lopez | Sprint 2 | EDI Integration | backend, edi, invoice, 3-way-match
EDI-4005 | Create daily EDI transmission batch job (BTH7010) | As a system, I need scheduled batch processing for EDI transmissions. Acceptance Criteria: - Daily transmission job for outbound 850 messages - Polling for inbound messages from VAN - Failed message retry with exponential backoff - Transmission status reporting - Archival of processed messages | 5 | Medium | To Do | E.Hill | Sprint 2 | Batch Processing | backend, batch, edi, scheduler
EDI-4006 | Design EDI transaction logging database | As a system, I need to log all EDI transactions for audit and troubleshooting. Acceptance Criteria: - Create TBL_EDI_LOG for transaction history - Create TBL_SUPPLIER_MAP for supplier EDI configuration - Store raw EDI messages - Transaction status tracking - Indexes on supplier_id, transaction_type, timestamp - Data retention (7 years for compliance) | 5 | High | To Do | F.Scott | Sprint 1 | Database | backend, database, edi, audit
EDI-4007 | Build supplier EDI onboarding tools | As a procurement manager, I need tools to onboard suppliers to EDI. Acceptance Criteria: - Supplier EDI capability assessment form - Trading partner configuration UI - Test message exchange capability - EDI mapping documentation generator - Supplier onboarding checklist tracker | 5 | Low | To Do | G.Green | Sprint 3 | Configuration | frontend, edi, onboarding, admin