## Estimate Summary
PROJECT ESTIMATION
|  |  |  | NOTE: | 1 Point = 6 hours
1 Story Point = $600
| Scope Item | Effort in Points | (%) | Category
Development Effort = Analysis + Build (Code & Unit Test) + Code Reviews
QA Effort = Analysis, Planning, Test case design, Test data creation, Execution
| Project Management - 30% of total Development effort |  |  | PM
| Technical Architecture - 12% of total Development effort |  |  | ARCH
| Defect Resolution Dev 8% of total Development effort |  |  | DEV
| Defect Resolution QA 8% of total QA effort |  |  | QA
| Regression Testing - 15% of total QA effort |  |  | QA
| Test Automation - 10% of total QA effort |  |  | QA
| Environment Setup - 3% of total Development effort |  |  | INFRA
| Performance Testing - 5% of total QA effort |  |  | QA
| Code Quality/Tech Debt - 10% of total Development effort |  |  | DEV
| Integration Testing | 12 |  | QA
| End to End Testing | 8 |  | QA
| Dev Support during Testing - 8% of total Development effort | 0 |  | DEV
| Post Go-Live Support - 10% of total effort | 0 |  | SUP
| Release Coordination - 3% of total Development effort |  |  | REL
| Deployment Activities - 4% of total Development effort |  |  | REL
| Infrastructure Setup - 5% of total Development effort |  |  | INFRA
| Documentation - 2% of total Development effort |  |  | DOC
| TOTAL Estimate (In Points): | 276.3 | 100.00%
Total Estimate ($):
| Total Dev Effort (In Points): | 135
Total Dev Effort ($):
| Total QA Effort (In Points): | 80
Total QA Effort ($):

## Task Breakdown
Ticket ID | Task Description | Story Points | Notes | Module Affected
| Carrier tracking aggregator SVC8010 Multi-carrier API integration Tracking event normalization | DEV: 35 Points QA: 20 Points | Multi-carrier | Tracking
| Notification dispatcher SVC8011 Email and SMS notifications Event-driven alerts | DEV: 25 Points QA: 15 Points | Email/SMS | Tracking
| Exception handler SVC8012 Delay detection Escalation workflows | DEV: 20 Points QA: 12 Points | Delay alerts | Tracking
| Customer tracking portal WEB8010 React frontend Real-time updates | DEV: 30 Points QA: 18 Points | React frontend | Web
| CS agent dashboard WEB8011 Internal tracking tool Case management integration | DEV: 25 Points QA: 15 Points | Internal tool | Web

## QA Estimates
QA Estimation Details
Total QA Points: | 80

## Dev Estimates
Development Estimation Details
Total Dev Points: | 135

## Assumptions and Risks
ASSUMPTIONS
• Carrier APIs available and documented
• Customer email/phone data accurate
• Notification service configured
• Customer service tools support integration
DEPENDENCIES
• Carrier API credentials obtained
• Email/SMS service provisioned
• Order fulfillment system integration
RISKS
Risk | Probability | Impact | Mitigation
Carrier API rate limits | Medium | Medium | Caching and batch requests
Notification delivery failures | Low | Medium | Retry logic and fallback channels
Customer privacy concerns | Low | High | Opt-in mechanism and clear privacy policy

## Sizing Guidelines
Story Point Sizing Guidelines
Points | Description
1-2 Points | Small, well-understood changes
3-5 Points | Medium complexity, some unknowns
6-8 Points | Complex changes, multiple components
9-13 Points | Very complex, requires research
13+ Points | Should be broken down into smaller stories

## Budget Summary
Budget Summary
Total Project Budget:
Development:
QA:

## Reference Data
Reference Data
Hourly Rate: $100
Points to Hours: 1 Point = 6 Hours
Story Point Value: $600

## Jira Stories
PRJ-10055 - Jira Stories
Story Key | Summary | Description | Story Points | Priority | Status | Assignee | Sprint | Component | Labels
TRK-5001 | Build carrier tracking aggregator service (SVC8010) | As a system, I need to integrate with multiple carrier APIs for real-time tracking. Acceptance Criteria: - Integration with FedEx, UPS, USPS tracking APIs - Tracking event normalization across carriers - Real-time webhook listeners for carrier updates - Fallback polling for carriers without webhooks - Caching strategy to respect rate limits - Error handling for carrier API downtime | 13 | High | To Do | H.Adams | Sprint 1 | Tracking Service | backend, carrier, api-integration, tracking
TRK-5002 | Implement notification dispatcher (SVC8011) | As a customer, I need to receive notifications about my shipment status. Acceptance Criteria: - Email notifications via SendGrid/SES - SMS notifications via Twilio - Event-driven notification triggers (shipped, in-transit, delivered, delayed) - Notification templates with shipment details - Opt-in/opt-out management - Notification history tracking | 8 | High | To Do | I.Baker | Sprint 1 | Notification Service | backend, notifications, email, sms
TRK-5003 | Create exception handler for delivery delays (SVC8012) | As an operations team, I need automated detection and escalation of delivery exceptions. Acceptance Criteria: - Delay detection based on expected delivery date - Exception classification (weather, carrier issue, address problem) - Escalation workflow to customer service - Proactive customer notification for delays - Exception metrics dashboard | 5 | Medium | To Do | J.Carter | Sprint 2 | Tracking Service | backend, exceptions, alerts, workflow
TRK-5004 | Build customer tracking portal (WEB8010) | As a customer, I need a web portal to track my shipments in real-time. Acceptance Criteria: - React-based tracking UI - Order lookup by order number or tracking number - Real-time shipment status display - Estimated delivery date/time - Shipment timeline with tracking events - Mobile-responsive design - Multi-language support | 13 | High | To Do | K.Mitchell | Sprint 2 | Frontend | frontend, react, tracking, customer-portal
TRK-5005 | Develop CS agent dashboard (WEB8011) | As a customer service agent, I need a dashboard to track all shipments and handle exceptions. Acceptance Criteria: - React-based internal dashboard - Search by customer, order, tracking number - Filter by shipment status and exceptions - Case management integration - Bulk shipment updates - Export to Excel for reporting - Real-time updates via WebSockets | 8 | Medium | To Do | L.Perez | Sprint 2 | Frontend | frontend, react, internal-tool, dashboard
TRK-5006 | Create tracking status refresh batch job (BTH8010) | As a system, I need scheduled batch updates for shipment tracking status. Acceptance Criteria: - Hourly polling for carriers without webhooks - Batch update processing - Stale tracking detection (no updates > 48 hours) - Rate limit management - Retry queue for failed updates | 5 | Medium | To Do | M.Roberts | Sprint 3 | Batch Processing | backend, batch, tracking, scheduler
TRK-5007 | Design tracking database schema | As a system, I need database tables for tracking events and notifications. Acceptance Criteria: - Create TBL_TRACKING for shipment tracking events - Create TBL_NOTIFICATION for notification history - Indexes on tracking_number, order_id, carrier, status - Partitioning by shipment_date - Data retention (90 days active, archive older) - Migration scripts | 5 | High | To Do | N.Turner | Sprint 1 | Database | backend, database, schema, tracking
TRK-5008 | Configure carrier API credentials and webhooks | As a system administrator, I need to configure carrier integrations. Acceptance Criteria: - Secure credential storage for carrier APIs - Webhook endpoint registration with carriers - API key rotation capability - Carrier-specific configuration (timeouts, retries) - Testing tools for carrier connectivity | 3 | High | To Do | O.Phillips | Sprint 1 | Configuration | backend, config, carrier, webhooks